## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
Sprint 1 | Sprint 1 | US01 | As a developer, I need to set up a Maven-based project structure so that dependencies can be managed efficiently. | MUST HAVE | Maven & Jakarta Libraries | Bishnu | 3- Completed
Sprint 1 | Sprint 1 | US02 | As a system admin, I want to configure the Tomcat server and deploy the WAR file to test servlet functionality. | MUST HAVE | Tomcat Server | Bishnu | 3- Completed
Sprint 1 | Sprint 1 | US03 | As a developer, I want to establish a database connection using JDBC to interact with the banking database. | MUST HAVE | MySQL Database | Bishnu | 3- Completed
Sprint 2 | Sprint 2 | US04 | As a user, I want to register my account so that I can perform transactions after logging in. | MUST HAVE | JDBC Connection & DAO Layer | Bishnu | 3- Completed
Sprint 2 | Sprint 2 | US05 | As a user, I want to log in securely using credentials so that unauthorized users cannot access my account. | MUST HAVE | Registration Module | Bishnu | 3- Completed
Sprint 2 | Sprint 2 | US06 | As a user, I want to view my account balance so that I can check available funds anytime. | SHOULD HAVE | Login & Account DAO | Bishnu | 3- Completed
Sprint 3 | Sprint 3 | US07 | As a user, I want to transfer money to another account so that I can make payments easily. | MUST HAVE | Account & Transaction Tables | Bishnu | 3- Completed
Sprint 3 | Sprint 3 | US08 | As a developer, I need to implement transaction history retrieval to allow users to view past transactions. | SHOULD HAVE | Transfer Module | Bishnu | 3- Completed
Sprint 3 | Sprint 3 | US09 | As a developer, I want to add exception handling and logging for all servlets to ensure system stability. | MUST HAVE | All Servlets | Bishnu | 3- Completed
Sprint 4 | Sprint 4 | US10 | As a developer, I want to expose REST APIs for account and transaction services to support future frontend integration. | COULD HAVE | Service Layer | Bishnu | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 91 | 49 | 32 | 10 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
US01 | T01 | Create Maven project and configure dependencies (Jakarta EE, JDBC, MySQL Connector) | 2025-09-15 | 2025-09-15 | Bishnu | Setup | Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US01 | T02 | Configure Tomcat 11 server and test initial deployment | 2025-09-16 | 2025-09-16 | Bishnu | Setup | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US03 | T03 | Create MySQL database schema for accounts & transactions | 2025-09-17 | 2025-09-17 | Bishnu | Database | Completed | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US03 | T04 | Implement DBConnectionUtil class for JDBC connectivity | 2025-09-18 | 2025-09-18 | Bishnu | Development | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US04 | T05 | Create DAO classes for User and Account entities | 2025-09-20 | 2025-09-20 | Bishnu | Development | Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US04 | T06 | Write SQL queries for insert, update and fetch operations | 2025-09-21 | 2025-09-22 | Bishnu | Database | Completed | 5 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US05 | T07 | Develop RegistrationServlet and LoginServlet controllers | 2025-09-23 | 2025-09-23 | Bishnu | Development | Completed | 8 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US05 | T08 | Implement password encryption and validation logic | 2025-09-25 | 2025-09-25 | Bishnu | Security | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US06 | T09 | Test DAO and Servlet integration with database | 2025-09-26 | 2025-09-26 | Bishnu | Testing | Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US07 | T10 | Create REST Controllers for User and Account CRUD | 2025-09-27 | 2025-09-27 | Bishnu | API Development | Completed | 6 | 2 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US08 | T11 | Configure centralized Exception Handling and Logging | 2025-09-28 | 2025-09-28 | Bishnu | Maintainence | Completed | 5 | 2 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US09 | T12 | Test backend using Postman for all endpoints | 2025-09-29 | 2025-09-29 | Bishnu | Testing | Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US10 | T13 | Initialize React project and install dependencies | 2025-09-30 | 2025-09-30 | Bishnu | Frontend Setup | Completed | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US11 | T14 | Setup React Router and project structure | 2025-10-01 | 2025-10-01 | Bishnu | Frontend Setup | Completed | 4 | 2 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US12 | T15 | Create reusable components (Navbar, Sidebar, Tabs) | 2025-10-02 | 2025-10-02 | Bishnu | Frontend Dev | Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US13 | T16 | Develop AccountTable & TransactionTable components | 2025-10-03 | 2025-10-03 | Bishnu | Frontend Dev | Completed | 7 | 2 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US14 | T17 | Implement CreateAccount and Transaction forms | 2025-10-04 | 2025-10-04 | Bishnu | Frontend Dev | Completed | 6 | 3 | 3 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US15 | T18 | Integrate frontend with backend REST APIs | 2025-10-05 | 2025-10-05 | Bishnu | Integration | Completed | 8 | 3 | 3 | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
US16 | T19 | Perform end-to-end testing (Postman + UI testing) | 2025-10-06 | 2025-10-06 | Bishnu | Testing | Completed | 4 | 4 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint 1 | DAY1 | Faced issues setting up Maven dependencies for Jersey and database libraries. | Updated pom.xml to include correct Jersey, Jackson, and MySQL dependencies; reloaded Maven project.
Sprint 1 | DAY3 | Errors during Jersey configuration (ResourceConfig not loading packages properly). | Verified package names in JerseyConfig, added @ApplicationPath("/api"), and ensured controller classes were correctly registered.
Sprint 1 | DAY5 | Couldn’t connect to MySQL database from the backend. | Checked JDBC URL, added driver dependency, and tested database connectivity through DAO layer.
Sprint 2 | DAY2 | CORS errors when connecting frontend (React) to backend API. | Manually registered CORS filter in JerseyConfig to allow frontend-origin requests.
Sprint 2 | DAY4 | JSON serialization issue (LocalDate not deserializing properly). | Added Jackson JavaTimeModule and configured object mapper in Jersey provider.
Sprint 2 | DAY5 | Difficulty testing REST APIs after schema updates. | Used Postman to validate all CRUD endpoints for User, Goal, Diet, and Workout APIs.
Sprint 3 | DAY1 | Data mismatch between frontend requests and backend JSON fields. | Updated React API call structures and ensured request/response mappings match DTOs.
Sprint 3 | DAY3 | Delays due to repeated fetch errors in the React frontend. | Implemented centralized API service with Axios and improved error handling.
Sprint 3 | DAY5 | UI not refreshing after performing delete/update operations. | Added state re-render logic in React using useEffect after API calls.
Sprint 4 | DAY2 | Deployment errors while running backend on Tomcat server. | Rebuilt .jar file using Maven, redeployed to Tomcat, and fixed port conflicts.
Sprint 4 | DAY4 | Frontend build not loading environment variables correctly. | Configured .env for API base URL and verified React build path.
Sprint 4 | DAY5 | Needed to finalize project documentation and testing checklist. | Completed documentation for REST endpoints, tested all CRUD operations, and reviewed final build.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | Sprint 1 | 2025-09-15 | 2025-09-20 |  | Follow proper Maven setup and dependency management | Stop skipping environment verification before coding | Continue detailed documentation for project setup | Created a proper Maven POM with all required Jakarta and JDBC dependencies; validated Tomcat deployment
2 | Sprint 1 | 2025-09-15 | 2025-09-20 |  | Perform basic REST testing after each configuration change | Stop deploying without testing the API endpoints | Continue collaboration during backend setup | Configured Tomcat and tested REST API endpoints through Postman before backend expansion
3 | Sprint 2 | 2025-09-21 | 2025-09-25 |  | Write optimized SQL queries and enable proper JDBC connection pooling | Stop using static connection objects in DAO | Continue following DAO pattern and reusability | Created separate DB utility class for connections and optimized SQL queries for performance
4 | Sprint 2 | 2025-09-21 | 2025-09-25 |  | Implement data validation and exception handling on backend | Stop ignoring input validation during form submission | Continue consistent REST API documentation | Added validation annotations and global exception handling using Jakarta
5 | Sprint 3 | 2025-09-26 | 2025-09-30 |  | Design frontend components with modular approach | Stop inline styling and duplicated code | Continue using Tailwind CSS utilities | Refactored components and created reusable UI elements like Navbar, Sidebar, and Tabs
6 | Sprint 3 | 2025-09-26 | 2025-09-30 |  | Improve communication between frontend and backend using Axios | Stop hardcoding API URLs | Continue using environment-based configurations | Implemented .env for API URLs and created Axios service wrapper for all API calls
7 | Sprint 4 | 2025-10-01 | 2025-10-05 |  | Test frontend and backend integration after every push | Stop manual data entry during testing | Continue frequent component testing | Created mock data for API calls and integrated automated tests for UI forms
8 | Sprint 4 | 2025-10-01 | 2025-10-05 |  | Automate database initialization for test environments | Stop using direct database modifications | Continue using migration scripts | Added init.sql and applied schema versioning for clean local testing setup