## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Bishnu Bhakat | 2025-09-15 | Maven dependencies not resolving for Jakarta Servlet API during project setup | Sprint 1 | Bishnu Bhakat | Standards | Updated pom.xml with correct Jakarta dependencies and versions | 2025-09-15 | Closed | Build Succesfully
2 | Bishnu Bhakat | 2025-09-17 | Database connection failed due to incorrect JDBC URL format | Sprint 1 | Bishnu Bhakat | Logical | Checked Db Connection Url | 2025-09-18 | Closed | Connection verified
3 | Bishnu Bhakat | 2025-09-19 | Tomcat deployment failed due to incorrect format and port | Sprint 1 | Bishnu Bhakat | Logical | Configure the Port and Url of Server | 2025-09-20 | Closed | Deployment verified
4 | Bishnu Bhakat | 2025-09-22 | DAO classes not closing ResultSet and PreparedStatement properly | Sprint 1 | Bishnu Bhakat | Maintainability | Implemented try-with-resources and ensured proper cleanup | 2025-09-22 | Closed | Verified via logging
5 | Bishnu Bhakat | 2025-09-24 | Duplicate user record inserted during registration | Sprint 2 | Bishnu Bhakat | Logical | Added pre-insert check for existing username/email | 2025-09-25 | Closed | Tested successfully
6 | Bishnu Bhakat | 2025-09-27 | NullPointerException when fetching non-existent account ID | Sprint 2 | Bishnu Bhakat | Logical | Added null-check and error handling in Service layer | 2025-09-27 | Closed | Verified through test case
7 | Bishnu Bhakat | 2025-10-06 | Exception handling inconsistent across servlets | Sprint 3 | Bishnu Bhakat | Maintainability | Centralized exception handling via ExceptionHandler class | 2025-10-06 | Closed | Refactored successfully
8 | Bishnu Bhakat | 2025-10-08 | Logging configuration missing, no server logs visible | Sprint 3 | Bishnu Bhakat | Maintainability | Configured Logs | 2025-10-08 | Closed | Logs verified
9 | Bishnu Bhakat | 2025-10-09 | REST APIs not returning proper HTTP status codes | Sprint 3 | Bishnu Bhakat | Standards | Implemented consistent status codes and messages | 2025-10-09 | Closed | API verified
10 | Bishnu Bhakat | 2025-10-10 | Error while initaiting Transactions | Sprint 3 | Bishnu Bhakat | Logical | Checked sender and reciecers account number for transactions | 2025-10-10 | Closed | Tested successfully
11 | Bishnu Bhakat | 2025-10-11 | Withdrawal operation allowing negative balance | Sprint 3 | Bishnu Bhakat | Logical | Added validation check before transaction commit | 2025-10-11 | Closed | Verified

## Sheet2
Logical
User Interface
Maintainability
Standards
Others